## Sheet1
Project 4 Name: |  | Increasing the number of children in the HNC in Quality Opportunities
Project Goals/Desired Outcomes: |  | The HNCs will build and develop high-quality preschool programs that enable children within their community to enter kindergarten prepared to succeed in school and in life.
Narrative: |  | The goal of this project is to meet the needs of the high needs community (HNC). Sub grantees within the HNC will collaborate to ensure Least Restrictive Environment, Child Find, Family Engagement, waiting list, comprehensive services, professional developement and Most In Need systems are in place.
Key Performance Measures: |  | Number of Eligible Children served in High Quality Preschool Programs funded by the grant, Percentage of Eligible Children served in High Quality Preschool Programs funded by the grant, Number of children served overall in the State Preschool Program, Percentage of children served overall in the State Preschool Program, Number of children in the High-Need Communities served by the grant that are ready for kindergarten as determined by the State's Kindergarten Entry Assessment or, if the State does not yet have a Kindergarten Entry Assessment, other valid and reliable means of determining school readiness, Number of children in the High-Need Communities served by the grant that are ready for kindergarten as determined by the State's Kindergarten Entry Assessment or, if the State does not yet have a Kindergarten Entry Assessment, other valid and reliable means of determining school readiness.
Selection Criterion Addressed: |  | (C)(1)(c) Supporting Children with Disabilities and English Language Learners, (C)(1)(d) Conducting a Needs Assessment, (C)(1)(I) Engaging parents and families, (C)(1)(j) Building Systems linkage to other early learning assessment system, (E)(9) Ensuring outreach to enroll isolated or hard- to-reach families; help families build protective, (E)(10) Ensuring strong partnership between Sub-grantees and LEA's or other Early Learning
Project Budget
PD/E Grant Funds: |  | 9182138.88 | Other Funds: | 0 |  | Overall Project Budget: |  | 9182138.88
Project 4 Activities
Code # | Type | Activities, Tasks, Deliverable, Subtask Name | Status | Start Date | End Date | Deliverable | Assignee (Responsible Individual) | Grantee Comments
4 | Project | Sub-grantees - Ensuring coordinated systems to provide high quality early childhood programming within the HNC | Not Started | [mm/dd/yy] | [mm/dd/yy]
4.1 | Activity | Increasing the Least Restrictive Environment (LRE) options for children | Not Started | 2015-07-01 | 2019-06-30 |  | ECPS
4.1.1 | Task | Schedule a meeting for all sub-grantees to discuss the expectations outlined in the PDG and current LRE continuum of placement options and identify . | Not Started | 2016-11-01 | 2016-12-31 |  | ECPS
4.1.2 | Task | Identify the local LRE continuum options for IEP teams and families based on the graphic organizer. | Not Started | 2017-01-01 | 2017-06-30 | yes | ECPS
4.1.3 | Task | IEP (Individualized Education Program) teams to work together with families to intentionally find the most-appropriate least restrictive environment placement for the child | Not Started | 2015-07-01 | 2016-06-30 |  | ECPS
4.1.4 | Task | Each sub-grantee will conduct a needs assessment to establish capacity for becoming an LRE placement option. | Not Started | 2016-07-01 | 2016-12-31 |  | ECPS
4.1.5 | Task | The ECPS will connect the sub-grantees with the inclusion coaching supports as appropriate. | Not Started | 2017-01-01 | 2017-06-30 |  | ECPS
4.1.6 | Task | Update and identify the local LRE continuum options for IEP teams and families based on the graphic organizer. | Not Started | 2018-01-01 | 2018-06-30 | yes | ECPS
4.1.7 | Task | IEP (Individualized Education Program) teams to work together with families to intentionally find the most-appropriate least restrictive environment placement for the child | Not Started | 2016-07-01 | 2017-06-30 |  | ECPS
4.1.8 | Task | New sub-grantees will conduct a needs assessment to establish capacity for becoming an LRE placement option. | Not Started | 2017-07-01 | 2017-12-31 |  | ECPS
4.1.9 | Task | The ECPS will connect any new sub-grantees with the inclusion coaching supports as appropriate. | Not Started | 2018-01-01 | 2018-06-30 |  | ECPS
4.1.10 | Task | Update and identify the local LRE continuum options for IEP teams and families based on the graphic organizer. | Not Started | 2019-01-01 | 2019-06-30 | yes | ECPS
4.1.11 | Task | IEP (Individualized Education Program) teams to work together with families to intentionally find the most-appropriate least restrictive environment placement for the child | Not Started | 2017-07-01 | 2018-06-30 |  | ECPS
4.1.12 | Task | New sub-grantees will conduct a needs assessment to establish capacity for becoming an LRE placement option. | Not Started | 2018-07-01 | 2018-12-31 |  | ECPS
4.1.13 | Task | The ECPS will connect any new sub-grantees with the inclusion coaching supports as appropriate. | Not Started | 2019-01-01 | 2019-06-30 |  | ECPS
4.2 | Activity | Creating a Child Find plan | Not Started | 2015-07-01 | 2019-06-30 |  | ECPS
4.2.1 | Task | Schedule an ECQUIP meeting for all sub- grantees to discuss legal and quality expectations of the Child Find process based on the HELP manual. | Not Started | 2015-07-01 | 2015-10-31 |  | ECPS
4.2.2 | Task | The HNC will analyze current Child Find marketing strategies | Not Started | 2015-11-01 | 2015-12-31 |  | ECPS
4.2.3 | Task | Create a robust plan for educating the community, families and staff about Child Find opportunities/ mandates. | Not Started | 2016-01-01 | 2016-06-30 | yes | ECPS
4.2.4 | Task | The HNC will create a common referral process for screening and evaluation for possible IDEA services. | Not Started | 2016-07-01 | 2016-12-31 | yes | ECPS
4.2.5 | Task | The ECPS will ensure that all staff within the HNC will receive training on the child find process, local referral procedures, and federal mandates. | Not Started | 2015-07-01 | 2015-08-30 |  | ECPS
4.2.6 | Task | The HNC will analyze pervious years child find marketing strategies | Not Started | 2016-11-01 | 2016-12-31 |  | ECPS
4.2.7 | Task | Revise the plan for educating the community, families, and staff about child find opportunities/ mandates. | Not Started | 2017-01-01 | 2017-06-30 | yes | ECPS
4.2.8 | Task | The HNC will review and revise the common referral process for screening and evaluation for possible IDEA services. | Not Started | 2017-07-01 | 2017-12-31 | yes | ECPS
4.2.9 | Task | The ECPS will ensure that all staff within the HNC will receive training on the child find process, local referral procedures, and federal mandates. | Not Started | 2016-07-01 | 2016-08-30 |  | ECPS
4.2.10 | Task | The HNC will analyze pervious years child find marketing strategies | Not Started | 2017-11-01 | 2017-12-31 |  | ECPS
4.2.11 | Task | Revise the plan for educating the community and families about child find opportunities/ mandates. | Not Started | 2018-01-01 | 2018-06-30 | yes | ECPS
4.2.12 | Task | The HNC will review and revise the common referral process for screening and evaluation for possible IDEA services. | Not Started | 2018-07-01 | 2018-12-31 | yes | ECPS
4.2.13 | Task | The ECPS will ensure that all staff within the HNC will receive training on the child find process, local referral procedures, and federal mandates. | Not Started | 2017-07-01 | 2017-08-30 |  | ECPS
4.2.14 | Task | The HNC will analyze pervious years child find marketing strategies | Not Started | 2018-11-01 | 2018-12-31 |  | ECPS
4.2.15 | Task | Revise the plan for educating the community and families about child find opportunities/ mandates. | Not Started | 2019-01-01 | 2019-06-30 | yes | ECPS
4.2.16 | Task | The HNC will review and revise the common referral process for screening and evaluation for possible IDEA services. | Not Started | 2019-07-01 | 2019-12-31 | yes | ECPS
4.2.17 | Task | The ECPS will ensure that all staff within the HNC will receive training on the child find process, local referral procedures, and federal mandates. | Not Started | 2018-07-01 | 2018-08-30 |  | ECPS
4.3 | Activity | Ensure all children served by the sub-grantees receive a comprehensive screening within 45 days. | Not Started | 2015-07-01 | 2016-06-30 |  | ECPS
4.3.1 | Task | The HNC will create a common screening process. | Not Started | 2016-07-01 | 2016-10-31 | yes | ECPS
4.3.2 | Task | The HNC will identify partners and resources available to provide vision, hearing, and oral health screenings. | Not Started | 2016-11-01 | 2017-01-31 |  | ECPS
4.3.3 | Task | Working in collaboration with the Child Care Health Consultant and the ECPS, the sub-grantees will coordinate and organize required screening to meet the deadline. | Not Started | 2017-02-01 | 2017-04-30 |  | ECPS
4.3.4 | Task | The HNC will review and revise their common screening process. | Not Started | 2017-07-01 | 2017-10-31 | yes | ECPS
4.3.5 | Task | The HNC will identify partners and resources available to provide vision, hearing, and oral health screenings. | Not Started | 2017-11-01 | 2018-01-31 |  | ECPS
4.3.6 | Task | Working in collaboration with the Child Care Health Consultant and the ECPS, the sub-grantees will coordinate and organize required screening to meet the deadline. | Not Started | 2018-02-01 | 2018-04-30 |  | ECPS
4.3.7 | Task | The HNC will review and revise their common screening process. | Not Started | 2018-07-01 | 2018-10-31 | yes | ECPS
4.3.8 | Task | The HNC will identify partners and resources available to provide vision, hearing, and oral health screenings. | Not Started | 2018-11-01 | 2019-01-31 |  | ECPS
4.3.9 | Task | Working in collaboration with the Child Care Health Consultant and the ECPS, the sub-grantees will coordinate and organize required screening to meet the deadline. | Not Started | 2019-02-01 | 2019-04-30 |  | ECPS
4.4 | Activity | Increase the transition rate between Part C to Part B (619) to 100% within the HNC. | Not Started | 2015-07-01 | 2019-06-30 |  | ECPS
4.4.1 | Task | The HNC will have representation from the local AzEIP provider on the ECQUIP team. | Not Started | 2016-07-01 | 2016-09-30 |  | ECPS
4.4.2 | Task | All sub-grantees will know and regularly meet with the local contact for AzEIP and preschool special education. | Not Started | 2016-10-01 | 2017-06-30 |  | ECPS
4.4.3 | Task | Sub-grantees will attend a collaborative meeting between AzEIP, local preschool special education director and state agencies regarding state changes to the transition process. | Not Started | 2017-01-01 | 2017-05-01 |  | ECPS
4.4.4 | Task | The ECPS will work with the LEA to ensure child find efforts are documented throughout the year. | Not Started | 2016-07-01 | 2017-06-30 |  | ECPS
4.4.5 | Task | The HNC will have representation from the local AzEIP provider on the ECQUIP team. | Not Started | 2017-07-01 | 2017-09-30 |  | ECPS
4.4.6 | Task | All sub-grantees will know and regularly meet with the local contact for AzEIP and preschool special education. | Not Started | 2017-10-01 | 2018-06-30 |  | ECPS
4.4.7 | Task | Sub-grantees will attend a collaborative meeting between AzEIP, local preschool special education director and state agencies regarding state changes to the transition process. | Not Started | 2018-01-01 | 2018-05-01 |  | ECPS
4.4.8 | Task | The ECPS will work with the LEA to ensure child find efforts are documented throughout the year. | Not Started | 2017-07-01 | 2018-06-30 |  | ECPS
4.4.9 | Task | The HNC will have representation from the local AzEIP provider on the ECQUIP team. | Not Started | 2018-07-01 | 2018-09-30 |  | ECPS
4.4.10 | Task | All sub-grantees will know and regularly meet with the local contact for AzEIP and preschool special education. | Not Started | 2018-10-01 | 2019-06-30 |  | ECPS
4.4.11 | Task | Sub-grantees will attend a collaborative meeting between AzEIP, local preschool special education director and state agencies regarding state changes to the transition process. | Not Started | 2019-01-01 | 2019-05-01 |  | ECPS
4.4.12 | Task | The ECPS will work with the LEA to ensure child find efforts are documented throughout the year. | Not Started | 2018-07-01 | 2019-06-30 |  | ECPS
4.5 | Activity | The sub-grantees will establish reciprocal relationships with families. | Not Started | 2015-07-01 | 2019-06-30 |  | ECPS
4.5.1 | Task | Schedule an ECQUIP meeting for all sub-grantees to discuss research based family engagement strategies. | Not Started | 2015-07-01 | 2015-10-31 |  | ECPS
4.5.2 | Task | Each sub-grantee will conduct a needs assessment related to current family engagement strategies | Not Started | 2015-11-01 | 2016-01-31 |  | ECPS
4.5.3 | Task | The sub-grantees will enhance the handbook given to families as they begin services and establish family engagement expectations. | Not Started | 2016-02-01 | 2016-05-31 | yes | ECPS
4.5.4 | Task | Schedule an ECQUIP meeting for all sub-grantees to review research based family engagement strategies and the requirement in the Program Guidelines for High Quality Early Education: Birth through Kindergarten. | Not Started | 2016-07-01 | 2016-10-31 |  | ECPS
4.5.5 | Task | The ECPS will provide professional development and technical assistance for local family engagement | Not Started | 2016-07-01 | 2017-06-30 |  | ECPS
4.5.6 | Task | The ECPS will work with the ECQUIP teams to write a family engagement plan for HNC | Not Started | 2017-01-01 | 2017-04-30 | yes | ECPS
4.5.7 | Task | ECQUIP Team will distribute the family engagement plan to all subgrantees within the HNC | Not Started | 2017-05-01 | 2017-06-30 |  | ECPS
4.5.8 | Task | The sub-grantees will enhance the handbook given to families as they begin services that include the family engagement plan and establishes family engagement expectations. | Not Started | 2018-03-01 | 2018-05-01 | yes | ECPS
4.5.9 | Task | Each sub-grantees will distribute the handbook to families as they begin services | Not Started | 2018-07-01 | 2019-06-30 |  | ECPS
4.5.10 | Task | The subgrantee will review and revise handbook if needed. | Not Started | 2019-03-01 | 2019-05-01 | yes | ECPS
4.6 | Activity | Establishing an HNC waiting list. | Not Started | 2015-07-01 | 2019-06-30 |  | ECPS
4.6.1 | Task | Schedule an ECQUIP meeting for all sub-grantees to create a common enrollment, recruitment, and wait list process. | Not Started | 2015-07-01 | 2015-08-30 | yes | ECPS
4.6.2 | Task | The HNC will operationlize a definition identifying children most in need. | Not Started | 2015-09-01 | 2015-10-31 | yes | ECPS
4.6.3 | Task | The ECPS will organize sub-grantee recruitment calendar. | Not Started | 2015-11-01 | 2015-12-31 | yes | ECPS
4.6.4 | Task | Each sub-grantee will work to create a simplified in-take process. | Not Started | 2015-07-01 | 2015-10-31 | yes | ECPS
4.6.5 | Task | Schedule an ECQUIP meeting for all sub-grantees to review and revise a common enrollment, recruitment, and wait list process. | Not Started | 2016-07-01 | 2016-08-30 | yes | ECPS
4.6.6 | Task | The HNC will review and revise the definition identifying children most in need. | Not Started | 2016-09-01 | 2016-10-31 | yes | ECPS
4.6.7 | Task | The ECPS will organize sub-grantee recruitment calendar. | Not Started | 2016-11-01 | 2016-12-31 | yes | ECPS
4.6.8 | Task | Each sub-grantee will work to review and revise the in-take process. | Not Started | 2016-07-01 | 2016-10-31 | yes | ECPS
4.6.9 | Task | Schedule an ECQUIP meeting for all sub-grantees to review and revise the common enrollment, recruitment, and wait list process. | Not Started | 2017-07-01 | 2017-08-30 | yes | ECPS
4.6.10 | Task | The HNC will review and revise the definition identifying children most in need. | Not Started | 2017-09-01 | 2017-10-31 | yes | ECPS
4.6.11 | Task | The ECPS will organize sub-grantee recruitment calendar. | Not Started | 2017-11-01 | 2017-12-31 | yes | ECPS
4.6.12 | Task | Each sub-grantee will work to review and revise the in-take process. | Not Started | 2017-07-01 | 2017-10-31 | yes | ECPS
4.6.13 | Task | Schedule an ECQUIP meeting for all sub-grantees to review and revise the common enrollment, recruitment, and wait list process. | Not Started | 2017-07-01 | 2017-08-30 | yes | ECPS
4.6.14 | Task | The HNC will review and revise the definition identifying children most in need. | Not Started | 2018-09-01 | 2018-10-31 | yes | ECPS
4.6.15 | Task | The ECPS will organize sub-grantee recruitment calendar. | Not Started | 2018-11-01 | 2018-12-31 | yes | ECPS
4.6.16 | Task | Each sub-grantee will work to review and revise the in-take process. | Not Started | 2018-07-01 | 2018-10-31 | yes | ECPS
4.7 | Activity | Researching sustainability options. | Not Started | 2017-07-01 | 2019-06-30 |  | ECPS
4.7.1 | Task | Schedule an ECQUIP meeting for all sub-grantees to discuss the sustainability of the preschool program. | Not Started | 2017-07-01 | 2017-12-31 |  | ECPS
4.7.2 | Task | Each sub-grantee will research what other funding opportunities are available in their HNC. | Not Started | 2018-01-01 | 2018-06-30 |  | ECPS
4.7.2.1 | Subtask | The HNC will identify partners to make access to quality early childhood experiences a priority in Arizona. | Not Started | 2018-04-01 | 2018-06-30 |  | HNC
4.7.2.2 | Subtask | Present preschool PDG successes to local School Boards. | Not Started | 2018-04-01 | 2018-06-30 |  | HNC
4.7.2.3 | Subtask | Present preschool PDG successes to local FTF Regional Councils. | Not Started | 2018-04-01 | 2018-06-30 |  | HNC
4.7.3 | Task | Schedule an ECQUIP meeting for all sub-grantees to discuss the sustainability of the preschool program. | Not Started | 2018-07-01 | 2018-12-31 |  | ECPS
4.7.4 | Task | Each sub-grantee will research what other funding opportunities are available in their HNC. | Not Started | 2019-01-01 | 2019-02-28 |  | ECPS
4.7.5 | Task | Each sub-grantee will create a plan to sustain the preschool program. | Not Started | 2019-03-01 | 2019-04-01 | yes | ECPS
4.7.5.1 | Subtask | The HNC will identify partners to make access to quality early childhood experiences a priority in Arizona. | Not Started | 2019-04-01 | 2019-06-30 |  | HNC
4.7.5.2 | Subtask | Present preschool PDG successes to local School Boards. | Not Started | 2019-04-01 | 2019-06-30 |  | HNC
4.7.5.3 | Subtask | Present preschool PDG successes to local FTF Regional Councils. | Not Started | 2019-04-01 | 2019-06-30 |  | HNC
4.8 | Activity | Establish a comprehensive service package for the HNC. | Not Started | 2015-07-01 | 2019-06-30 |  | ECPS
4.8.1 | Task | Schedule an ECQUIP meeting for all sub-grantees to discuss current comprehensive service within the HNC. | Not Started | 2017-01-01 | 2017-03-31 |  | ECPS
4.8.2 | Task | Create a graphic organizer or menu to illustrate the comprehensive service options available within the HNC. | Not Started | 2017-04-01 | 2017-04-30 | yes | ECPS
4.8.3 | Task | Each sub-grantees will idenify gaps in comprehensive services. | Not Started | 2017-05-01 | 2017-05-31 |  | ECPS
4.8.4 | Task | The ECPS and FTF Consultants will work to connect sub-grantees with the targeted services needed to address the gaps. | Not Started | 2017-06-01 | 2017-06-30 |  | ECPS
4.8.5 | Task | Schedule an ECQUIP meeting for all sub-grantees to discuss current comprehensive service within the HNC. | Not Started | 2018-01-01 | 2018-03-31 |  | ECPS
4.8.6 | Task | Create a graphic organizer or menu to illustrate the comprehensive service options available within the HNC. | Not Started | 2018-04-01 | 2018-04-30 | yes | ECPS
4.8.7 | Task | Each sub-grantees will idenify gaps in comprehensive services. | Not Started | 2018-05-01 | 2018-05-31 |  | ECPS
4.8.8 | Task | The ECPS and FTF Consultants will work to connect sub-grantees with the targeted services needed to address the gaps. | Not Started | 2018-06-01 | 2018-06-30 |  | ECPS
4.8.9 | Task | Create/Review and revise the graphic organizer or menu to illustrate the comprehensive service options available within the HNC. | Not Started | 2019-04-01 | 2019-04-30 | yes | ECPS
4.8.10 | Task | Each sub-grantees will idenify gaps in comprehensive services. | Not Started | 2019-05-01 | 2018-05-31 |  | ECPS
4.8.11 | Task | The ECPS and FTF Consultants will work to connect sub-grantees with the targeted services needed to address the gaps. | Not Started | 2019-06-01 | 2019-06-30 |  | ECPS
4.9 | Activity | Ensure all sub-grantee directors participate in Program Guidelines professsional development opportunities and implementation. | Not Started | 2015-07-01 | 2019-06-30 |  | ECPS
4.9.1 | Task | ADE will organize the Introduction to the Program Guidelines professional development opportunity within the HNC or each sub-grantees may participate in the online Introduction to the Program Guidelines. | Not Started | 2015-07-01 | 2016-06-30 |  | Lauren Zbyszinski
4.9.2 | Task | ADE will organize each Program Guidelines module professional development within the HNC or may participate in the online professional development. | Not Started | 2015-07-01 | 2019-06-30 |  | Lauren Zbyszinski
4.9.3 | Task | Module #1 Program Administation and Qualitfication | Not Started | 2016-01-01 | 2016-05-30 |  | ECPS
4.9.4 | Task | Module #2 Daily Routines and Schedules | Not Started | 2016-07-01 | 2016-12-31 |  | ECPS
4.9.5 | Task | Module #3 Program Practices | Not Started | 2017-01-01 | 2016-05-30 |  | ECPS
4.9.6 | Task | Module #4 Linguistic and Cultural Integration | Not Started | 2017-07-01 | 2017-12-31 |  | ECPS
4.9.7 | Task | Module #5 Family Engagement and Support | Not Started | 2015-07-01 | 2015-12-31 |  | ECPS
4.9.8 | Task | Module #6 Health and Nutrition | Not Started | 2018-01-01 | 2018-05-30 |  | ECPS
4.9.9 | Task | Module #7 Community Outreach and Collaboration | Not Started | 2018-07-01 | 2018-12-31 |  | ECPS
4.9.10 | Task | Module #8 Program Evaluation | Not Started | 2019-01-01 | 2019-05-30 |  | ECPS
4.10.0 | Activity | Ensure a professional development plan is created and implemented for the HNC. | Not Started | 2015-07-01 | 2019-06-30 |  | ECPS
4.10.1 | Task | Sub-grantees will participate in a survey to identify professional development needs within their program. | Not Started | 2015-07-01 | 2015-08-30 |  | ECPS
4.10.2 | Task | The ECPS will create a professional development plan for each HNC based on the survey results. | Not Started | 2015-09-01 | 2015-10-01 | yes | ECPS
4.10.3 | Task | The ECPS will organize professional development in the HNC. | Not Started | 2015-10-02 | 2016-06-30 |  | ECPS
4.10.4 | Task | ADE in collaboration with partners will provide professional development on the Part C to Part B | Not Started | 2015-10-02 | 2016-06-30 |  | ECPS
4.10.5 | Task | Sub-grantees will participate in a survey to identify professional development needs within their program. | Not Started | 2016-07-01 | 2016-08-30 |  | ECPS
4.10.6 | Task | The ECPS will create a professional development plan for each HNC based on the survey results. | Not Started | 2016-09-01 | 2016-10-01 | yes | ECPS
4.10.7 | Task | The ECPS will organize professional development in the HNC. | Not Started | 2016-10-02 | 2017-06-30 |  | ECPS
4.10.8 | Task | ADE in collaboration with partners will provide professional development on the Part C to Part B | Not Started | 2016-10-02 | 2017-06-30 |  | Nicol Russell
4.10.9 | Task | Sub-grantees will participate in a survey to identify professional development needs within their program. | Not Started | 2017-07-01 | 2017-08-30 |  | ECPS
4.10.10 | Task | The ECPS will create a professional development plan for each HNC based on the survey results. | Not Started | 2017-09-01 | 2017-10-01 | yes | ECPS
4.10.11 | Task | The ECPS will organize professional development in the HNC. | Not Started | 2017-10-02 | 2018-06-30 |  | ECPS
4.10.12 | Task | ADE in collaboration with partners will provide professional development on the Part C to Part B | Not Started | 2017-10-02 | 2018-06-30 |  | ECPS
4.10.13 | Task | Sub-grantees will participate in a survey to identify professional development needs within their program. | Not Started | 2018-07-01 | 2018-08-30 |  | ECPS
4.10.14 | Task | The ECPS will create a professional development plan for each HNC based on the survey results. | Not Started | 2018-09-01 | 2018-10-01 | yes | ECPS
4.10.15 | Task | The ECPS will organize professional development in the HNC. | Not Started | 2018-10-02 | 2019-06-30 |  | ECPS
4.10.16 | Task | ADE in collaboration with partners will provide professional development on the Part C to Part B | Not Started | 2018-10-02 | 2019-06-30 |  | ECPS
4.11 | Activity | Ensure the sub-grantees provide/input high quality ongoing progress monitoring into state board approved assessment tool. | Not Started | 2015-07-01 | 2019-06-30 |  | ECPS
4.11.1 | Task | All instructional staff within the sub-grantees will take the state board approved tool training. | Not Started | 2015-07-01 | 2015-09-01 |  | ECPS
4.11.2 | Task | All instructional staff within the sub-grantees will take the interrater reliability certification. | Not Started | 2016-01-01 | 2016-05-31 |  | ECPS
4.11.3 | Task | Leadership will create an assessment system plan. | Not Started | 2015-07-01 | 2015-09-30 | yes | ECPS
4.11.4 | Task | Schedule an ECQUIP meeting for all sub-grantees to discuss ways to improve their current assessment system based on the ECE assessment manual. | Not Started | 2015-10-01 | 2015-12-31 |  | ECPS
4.11.5 | Task | ADE will organize professional development strand for effective assessment systems in the HNC. | Not Started | 2016-01-01 | 2016-06-30 |  | ECPS
4.11.6 | Task | The ECPS will work with each director within the HNC to monitor for quality using the Child Observations and Portfolio Rubric. | Not Started | 2016-07-01 | 2017-06-30 |  | ECPS
4.11.7 | Task | All new instructional staff within the sub-grantees will take the state board approved tool training. | Not Started | 2016-07-01 | 2016-09-01 |  | ECPS
4.11.8 | Task | All new instructional staff within the sub-grantees will take the interrater reliability certification. | Not Started | 2017-01-01 | 2017-05-31 |  | ECPS
4.11.9 | Task | Leadership will review and revise their current assessment system plan. | Not Started | 2016-07-01 | 2016-09-30 | yes | ECPS
4.11.10 | Task | Schedule an ECQUIP meeting for all sub-grantees to discuss ways to improve their current assessment system based on the ECE assessment manual. | Not Started | 2016-10-01 | 2016-12-31 |  | ECPS
4.11.11 | Task | ADE will organize professional development strand for effective assessment systems in the HNC for new staff. | Not Started | 2017-01-01 | 2017-06-30 |  | ECPS
4.11.12 | Task | The ECPS will work with each new director within the HNC to monitor for quality using the Child Observations and Portfolio Rubric. | Not Started | 2017-07-01 | 2018-06-30 |  | ECPS
4.11.13 | Task | All new instructional staff within the sub-grantees will take the state board approved tool training. | Not Started | 2017-07-01 | 2017-09-01 |  | ECPS
4.11.14 | Task | All new instructional staff within the sub-grantees will take the interrater reliability certification. | Not Started | 2018-01-01 | 2018-05-31 |  | ECPS
4.11.15 | Task | Leadership will review and revise their current assessment system plan. | Not Started | 2017-07-01 | 2017-09-30 | yes | ECPS
4.11.16 | Task | Schedule an ECQUIP meeting for all sub-grantees to discuss ways to improve their current assessment system based on the ECE assessment manual. | Not Started | 2017-10-01 | 2017-12-31 |  | ECPS
4.11.17 | Task | ADE will organize professional development strand for effective assessment systems in the HNC for new staff. | Not Started | 2018-01-01 | 2018-06-30 |  | ECPS
4.11.18 | Task | The ECPS will work with each new director within the HNC to monitor for quality using the Child Observations and Portfolio Rubric. | Not Started | 2018-07-01 | 2019-06-30 |  | ECPS
4.11.19 | Task | All new instructional staff within the sub-grantees will take the state board approved tool training. | Not Started | 2018-07-01 | 2018-09-01 |  | ECPS
4.11.20 | Task | All new instructional staff within the sub-grantees will take the interrater reliability certification. | Not Started | 2019-01-01 | 2019-05-31 |  | ECPS
4.11.21 | Task | Leadership will review and revise their current assessment system plan. | Not Started | 2018-07-01 | 2018-09-30 | yes | ECPS
4.11.22 | Task | Schedule an ECQUIP meeting for all sub-grantees to discuss ways to improve their current assessment system based on the ECE assessment manual. | Not Started | 2018-10-01 | 2018-12-31 |  | ECPS
4.11.23 | Task | ADE will organize professional development strand for effective assessment systems in the HNC for new staff. | Not Started | 2019-01-01 | 2019-06-30 |  | ECPS
4.11.24 | Task | The ECPS will work with each new director within the HNC to monitor for quality using the Child Observations and Portfolio Rubric. | Not Started | 2019-01-01 | 2019-06-30 |  | ECPS
4.12 | Activity | Literacy continuum | Not Started | 2015-07-01 | 2019-06-30 |  | ECPS
4.12.1 | Task | ECPS will provide PD to new staff on "Developing a Thriving Reader from the Early Years: A Continuum of Effetive Literacy Practices" within each HNC. | Not Started | 2017-07-01 | 2017-09-30 |  | ECPS
4.12.2 | Task | The ECPS and ECQUIP Team review the district K-12 Literacy Plan and determine a plan for Birth to 5 within the HNC. | Not Started | 2017-10-01 | 2017-12-31 |  | ECPS
4.12.3 | Task | ECQUIP Team will distribute Birth to 5 Literacy plan within HNC. | Not Started | 2018-01-01 | 2018-03-31 | yes | ECPS
4.12.4 | Task | ECPS will provide PD to new staff on "Developing a Thriving Reader from the Early Years: A Continuum of Effetive Literacy Practices" within each HNC. | Not Started | 2018-07-01 | 2018-09-30 |  | ECPS
4.12.5 | Task | The ECPS and ECQUIP Team review the district K-12 Literacy Plan and determine a plan for Birth to 5 within the HNC. | Not Started | 2018-10-01 | 2018-12-31 |  | ECPS
4.12.6 | Task | ECQUIP Team will distribute Birth to 5 Literacy plan within HNC. | Not Started | 2018-01-01 | 2018-03-31 | yes | ECPS
4.13 | Activity | Empower- Growing Healthy Children | Not Started | 2015-07-01 | 2019-06-30 |  | ECPS
4.13.1 | Task | ECPS will assist subgrantees within the HNC to enroll in the Empower Program | Not Started | 2015-07-01 | 2015-10-31 |  | ECPS
4.13.2 | Task | ECPS will assist subgrantees within the HNC to write their statements of intent or commitment to each of the ten standards within the Empower program | Not Started | 2015-11-01 | 2015-12-30 | yes | ECPS
4.13.3 | Task | ECPS will assist new subgrantees within the HNC to enroll in the Empower Program | Not Started | 2016-07-01 | 2016-10-31 |  | ECPS
4.13.4 | Task | ECPS will assist new subgrantees within the HNC to write their statements of intent or commitment to each of the ten standards within the Empower program | Not Started | 2016-11-01 | 2016-12-30 | Yes | ECPS
4.13.5 | Task | ECPS will assist new subgrantees within the HNC to enroll in the Empower Program | Not Started | 2017-07-01 | 2017-10-31 |  | ECPS
4.13.6 | Task | ECPS will assist new subgrantees within the HNC to write their statements of intent or commitment to each of the ten standards within the Empower program | Not Started | 2017-11-01 | 2017-12-30 | Yes | ECPS
4.13.7 | Task | ECPS will assist new subgrantees within the HNC to enroll in the Empower Program | Not Started | 2018-07-01 | 2018-10-31 |  | ECPS
4.13.8 | Task | ECPS will assist new subgrantees within the HNC to write their statements of intent or commitment to each of the ten standards within the Empower program | Not Started | 2018-11-01 | 2018-12-30 | Yes | ECPS
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started