# Self-Assessment Tracking Form

| Required Completion Date | Performance Task | Actual Completion Date |
| --- | --- | --- |
| No later than 8/25/2025 | - SSIP PEAs submit completed Success Gaps Rubric and Action Plan |  |
| No later than 9/15/2025 | - PEA selects student files to be reviewed that are a representative sample of the district/charter - PEA submits the list of students to the PSM specialist using the Student Selection List |  |
| No later than 9/22/2025 | - PSM specialist provides feedback to PEA on the Student Selection List - SSIP PEAs receive feedback from PSM specialists for the Success Gaps Rubric and Action Plan Feedback Guide |  |
| No later than 10/1/2025 | - SSIP PEAs submit the Literacy Screener Data Form—Fall to PSM Specialist |  |
| Week of 10/27/2025 | - Meet (virtual/in-person) with PSM specialists to discuss the status of monitoring activities |  |
| 12/8/2025 | - SSIP PEAs complete SSIP and Walk through surveys |  |
| 12/19/2025 | - PEA submits copies of completed documentation to PSM specialist to include: child find worksheet(s), agency forms, In by 3 worksheet(s), and student forms - PEA submits completed outcome focus area and action plan to PSM specialist electronically (does not include SSIP PEAs) |  |
| No later than 1/16/2026 | - Meet with PSM specialist to discuss trends from student forms, statewide trends, and the student file selection to be submitted on Jan. 30 |  |
| No later than 1/30/2026 | - PEA submits student files to PSM specialist |  |
| No later than 2/27/2026 | - PSM specialist will provide verification feedback to the PEA on compliance calls and whether a follow-up visit is required in May - PSM specialist provides feedback on the outcome focus area analysis and action plan (does not include SSIP PEAs) |  |
| No later than 4/27/26 | - SSIP PEAs submit completed Success Gaps Rubric and Action Plan to PSM Specialist |  |
| No later than 5/18/2026 | - PSM specialist will conduct a follow-up visit, if needed, to verify corrections of noncompliance and review subsequent files (if needed) - PEA submits outcome focus area analysis and action plans (does not include SSIP PEAs) |  |
| No later than 6/1/2026 | - SSIP PEAs submit Literacy Screener Spring data - SSIP PEAs receive feedback from PSM specialist on the Analysis and Action Plan |  |
| No later than 6/6/2026 | - PEA receives successful completion letter or WNOF and completes CAP, if applicable |  |